STANDARD GUIDELINES

AND

FORMULA FOR PRICE ADJUSTMENT

Ist Edition

July, 2002

PAKISTAN ENGINEERING COUNCIL ISLAMABAD

Transparency International Pakistan has incorporated the procedures prescribed in the  PSML  Procurement Manual and is in conformity with the Public Procurement Rules 2004 and National Anticorruption Strategy NACS 2002. Authority means PPRA and Procuring Agency means PSML

September 2004

ACKNOWLEDGMENT

Pakistan Engineering Council extends deep appreciations and acknowledges the tremendous contribution in developing and finalizing this document by the following members of the Standards and Quality Committee:-

1.   Engr. M. Mazhar-ul Islam                                                                        - Convenor

(Chief Engineer (Contracts), NESPAK, Lahore)

2.   Engr. Prof. Dr. Shafaqat Nawaz                                                              - Member

(Director, Institute of Chemical Engg. & Tech.,  Punjab University, Lahore)

3.   Engr. Dr. Rafiq-ur-Rehman                                                                     - Member

(Director, Agricultural Mechanization Research Institute (AMRI), Multan)

4.   Engr. Prof. Dr. Bhawani Sankar                                                               - Member

(Professor & Chairman; Dept. of Electronics &  Telecommunication Engineering, Mehran Univ. of Eng. & Tech. , Jamshoro)

5.   Engr. Syed Ali Akbar Shah                                                                     - Member

(Project Director (Housing), Hyderabad Development Authority, Hyderabad)

6.   Engr. Tafsir Ahmad Khan                                                                        - Member

(Dy. Director (Electrical), Pakistan Standards & Quality

Control Authority (PSQCA), Karachi)

7.   Engr. Naveed-ul-Haq                                                                              - Member

(Engineer-In-charge, PTV, Quetta)

8.   Engr. Ahtisham-ul-Haq                                                                            - Member

(Director Development Planning, Central Development Region, Lahore)

9.   Engr. Syed Ehtesham Hussain                                                                  - Member

(Chief Executive, Precision Product Industries, Karachi)

10. Engr. Jilani Yousuf                                                                                   - Member

(Mechanical Engineer, National Refinery Ltd., Karachi)

11. Engr. M. Anwar Qaseem Qureshi                                                            - Member

(Assistant Director (T), WAPDA, Lahore)

12. Engr. Balal A. Khwaja                                                                             - Expert

(M/s Engineering Contracts Advisors Corporate Affairs Consultants, Karachi)

13. Engr. Rafique Gaya                                                                                  - Expert

(Partner, Gaya Construction Company (GCL), Karachi)

14. Engr. Syed Hamid Hassan, Ghazi Barotha                                                -  Expert

(Dy. Construction Manager, Ghazi Barotha Hydropower Project, Attock)

PREFACE

Pakistan  Engineering  Council  the  Statutory  Regulatory  body  entrusted  to  regulate  the engineering profession of Pakistan has undertaken among others, the standardization of

"Country specific" documents to regulate and streamline the hiring of engineering consultancy services and procurement of works. Standard Guidelines and Formula for Price Adjustment is one such document prepared by a team of experts comprising Employers, Constructors and Consultants in line with the instruction of Planning Commission in 1996. It is expected that use of this document will provide a reasonable basis for calculating price adjustment for construction contracts.

The following documents have been referred to in preparation of this document:

   FIDIC Conditions of Contract - 1999

   Ministry of Housing and Works, Government of Pakistan  - Proposal for Escalation,

1996

   O.M. No.F 3(9)-R-12/75 dated 30th September 1975.

Pakistan  Engineering  Council  wishes  to  place  on  record  its  deep  appreciation  for  the tremendous  work  done  by  the  Standards  and  Quality  Committee,  PEC  and  Gaya Construction Company, Karachi, for drafting this document.

Various Engineering Organizations and Departments are requested to use this document for calculating price adjustment in contracts. Any suggestions to improve this document are welcome which may please be addressed to:

Registrar

Pakistan Engineering Council Ataturk Avenue (East) Sector G-5/2

Islamabad

Tel # 92-51-2276225

Fax # 92-51-2276224

E-mail: registrar @ pec.org.pk

INSTRUCTIONS TO USERS

Background:

The provision of Price Adjustment on account of increase or decrease in costs of goods and services in construction contracts is practiced world over to have better competitive bids and execution of contracts on equitable and just manner. Prices of goods and labour are highly variable due to fluctuations in the currency market. Construction experts, therefore, thought it prudent to compute the cost of contracts on present price keeping provision of price adjustments for probable fluctuations.

In Pakistan, Finance Division has given the guidelines and formula for calculating  Price Adjustment through Office Memorandums (OM’s), Pak-PWD periodically prepared graphs for escalation for typical Civil, Mechanical and Electrical projects for compensation to the contractors. Similarly in 1996, Government of Pakistan (GoP) also issued a consolidated formula to simplify computation of Price Adjustment. Internationally reputed consultants continued to use provisions of FIDIC. However, keeping in view all the methods and practices, PEC prepared the document   - “Standard Guidelines and Formula for  Price Adjustment”, primarily  on the basis of rate analysis of various items in a contract. This document  when  debated,  felt  the  necessity  to  discuss  the  issue  with  the  stakeholders involving constructors, consultants, GoP officials and financial experts. Accordingly, a two days National Workshop was arranged in PEC HQs on March 30 & 31, 2000 where the basic  criteria  of  adopting  the  formula  method  in  line  with  FIDIC  was  decided.  This document is thus based on the said workshop recommendations.

Objectives:

This document is intended to  give reasonable compensation to the contractor, which by virtue of its being restricted to listed escalable items, is an approximation. The objectives of this document are to:

(a)       To make price adjustment as close as possible to the actual.

(b)       To set out a simple procedure.

(c)        To minimize ambiguities.

(d)       To make the contract more equitable.

How to Use:

1.         The user of this document is not to change any  provision hereof  unless otherwise stated in these Instructions.

2.         No other method, other than given in this document, is acceptable to compute the price adjustment.

3.         This  Guidelines  is  to  assist  the  users  for  preparation  of  provisions  for  price adjustment in their bidding/contract documents.

TABLE OF CONTENTS

DESCRIPTION                                                             PAGE NO.

PART-1:         GUIDELINES

A:         APPLICABILITY                                                  6

B:         PARAMETERS                                                     7

C:         PROCEDURE                                                        8

PART-2:         FORMULA                                                                          9

PART 1
GUIDELINES

A.        APPLICABILITY

1.         The provisions for price adjustment shall be applicable to the projects to be executed. For the ongoing contracts, the existing provisions provided in the contract shall continue to apply.

2.         Only contracts having duration of more than  twelve (12) months should be liable to price adjustment. Contracts of less than twelve months duration will be considered as fixed price contracts.

3.         Construction schedule should be provided by the contractor as required in the Contract.  Price adjustment shall be applicable  is payable in full for the original scheduled completion period.

4.         In  the  event  the  completion  of  contract  exceeds  the  original  scheduled period:

(i)         in case of default on the part of the contractor causing delay in original scheduled completion, the rate of  price adjustment  will be frozen at the original schedule date of completion, however  price adjustment will be applicable till actual completion. While computing price adjustment  beyond the scheduled completion period, in the event the rate is reduced, the reduced rate will apply.

(ii)        the price adjustment will be payable in full for the extended period if the contractor has not defaulted in causing the delay.

5.         Unless specifically stated otherwise in the contract, the compensation will apply to only those elements, which are specifically listed as escalable in the tender  documents.  This  list  will  specify  the  items  for  Civil,  Electrical, Mechanical, Sanitary, HVAC, etc. separately.

6.         Formula for  Price Adjustment provided herein will be applicable for all the contracts such as civil, electrical, mechanical etc. A list of commonly known items subject to Price Adjustment are provided below. User of the formula may add or delete any element  as deemed appropriate. They would then decide on the coefficients for the elements.

6.1       Some of the typical items for price adjustment are listed as under:

(i)         Cement

(ii)        Steel

(iii)       POL

(iv)       Labour Skilled

(v)        Labour unskilled

(vi)       Bitumen

7.         Financial  compensation  for  the  items  classified  as  above  shall  not  be considered again due to provision of Subsequent Legislation, if separately specified in the contract.

8.         There shall be no  price adjustment  for items that the Employer has either supplied free of cost or at fixed prices.

9.         This  document  will  be  applicable  to  all  contracts  including  Item  Rate Contracts, Lump Sum Contracts and %age over Schedule Contracts but excluding fixed price contract.

10.       This document will be applicable only for price adjustment in local currency

(Pak. Rs.). Price Adjustment in foreign currency is not in purview of this document which, if applicable, is to be finalized with mutual agreement among the parties in the Contract.

B.        PARAMETERS

1.         Base Date

The Base date for the cost of any item of work shall be the cost of the element of the item which was prevalent twenty eight (28) days prior to the date of submission of the tender.

2.         Effective Date

The  effective  date  of  fixing  the  fluctuating  rate  of  the  items  for price adjustment shall be twenty eight (28) days prior to the start of the execution month for which the contractor executed the item. The unit of time shall be a calendar month.

3.         Source of Prices

The prices of  elements  subject to price adjustment  shall be to the extent possible as given in the Statistical Bulletins published by Statistical Division of Government of Pakistan. Where available, statutory notifications and official price from public sector organizations may be used at the option of the Employer.  However, for a particular escalable item(s), the same source should be used throughout the currency of contract.

C.        PROCEDURE

1.         The billed amount the Works for each calendar month will be obtained from the checked bills submitted by the Contractor. In case the billed amount is for more than one month, the amount of the bill shall be  segregated for actual work done in each month.

2.         The  Base  Date  prices  and  the  Effective  Date  prices  shall  be  as  per guidelines B1 and B2 provided hereinbefore.

3.         The source for the prices will be as per guideline B3 provided hereinbefore.

4.         The  price adjustment  in the  billed amount  will then be calculated for the month   under   consideration   in   accordance   with   Formula   for   Price Adjustment.

PART 2: FORMULA

1.         The  formula  expressed  herebelow  is  a  format  in  its  generalized  form.  The Employer/user shall at the time of preparation of their bidding/tender documents shall determine the proportions of A, b, c, d, ……….. by appropriate rate analysis following the procedure enumerated in this document.

Formula For Price Adjustment:

Pn      =  A + b Ln + c Mn + d En +................

Lo       Mo       Eo

“Pn”       is  the  Price  Adjustment  factor for the work carried out in the period “n”

“A”         is the Non-Adjustable Portion of Contract Price

“b,c,d.........” are Coefficients or weightages for each specified item of escalation in the Contract.

“Ln, Mn, En.......”  are the Effective Date Prices (current prices) of escalable items for the period “n”.

“Lo,Mo,Eo........” are the Base Date Prices for the specified items

If “P” is the amount payable (prior to adjustment) at the rates entered in the Price Schedule of the work carried out in period “n” then, Adjusted (revised) amount payable to the Contractor for work carried out in the period “n” = PxPn.

2.         The base  date and effective date  prices of the specified item(s) shall be obtained from the sources specified in the contract.

3.         Specified Items subject to Price Adjustment.

The major items for highway and bridge construction would be POL, Labour, Cement, Steel and Bitumen whereas those for building projects would be POL, Labour,  Cement,  Steel  and  other  major  items depending on the nature of the project. Similarly, major items for other types of projects can be identified in the contract.

4.         Co-efficient or Weightages

The  Co-efficient  for  each  specified  item  shall  be  calculated  and  given  in  the bidding/tender documents. The co-efficient for each specified escalable item shall be

determined by the user proportionate to its ratio among all the escalable items in a contract.  The  sum  of  these  co-efficient shall form the adjustable portion of the Contract.

5.         Adjustable Portion of the Contract

The adjustable portion of the Contract shall generally be fixed between 0.35 to 0.55

(35%  to  55%)  depending  on  the  nature  of  the  project  and  discretion  of  the

Employer. Non-adjustable portion shall, thereby, not be generally less than 45%.

6.         Sources for Price Adjustment

Source of Base  Date and Effective Date  Prices shall be as stipulated at item-B3

hereabove. If any other source is used, it must be clearly stated in the Contract.

7.         Price Adjustment for Lumpsum Contract.

Formula of Price Adjustment for lumpsum contract provided at Item-1 above of this document  shall  be  used  in  determining  Price  Adjustment  for  contracts  having detailed breakdown of costs. However, when a contract is assigned on lump sum basis without detailed breakdown of quantities and costs, Price Adjustment for the specified   items   in   the   contract   will   be   computed   on   simple   derivation, increase/decrease in cost = Current Price - Base Price.

Base Price

If the result is (+ve), the price should be added to the contractor’s payable amount. If the result is (-ve), the price should be subtracted from the payable amount.

Quantities of the items subject to Price Adjustment can be obtained from the actual measurement or from certified invoice of the contractor or any other mode agreed between the parties.